## lab2
Summery of Development cost for Stratosphere
Expense category | Amount
Salaries
Project Manager(x1) | 14080
Business Analyst(x1) | 18720
Programmer/Developer(x1) | 23040
Systems Analys(x1) | 19200
Support Technician (x1) | 10800
Equipment (inclde software & hardware) | 5000
Traning | 3000
Facilities | 2000
Utilities | 2000
Travel/miscellaneous | 1000
Licenses | 2000
Total | 100840

## 2.1
Time Estimate for Nami Sushi Project
Subsystem | Functional Requirements | Iterations Required | Estimated Time
Dine-in ordering subsystem | 5 | 6 | 4 weeks
Takeaway ordering subsystem | 3 | 4 | 2 weeks
Cashier subsystem | 3 | 4 | 1 weeks
Inventory management subsystem | 3 | 4 | 1 weeks
Total development time |  |  | 8 weeks
System testing |  | 1 | 1 weeks
User acceptance test |  | 1 | 1 weeks
Total Project time |  |  | 10 weeks

## 2.2
Summery of Development cost for Nami Sushi
Expense category | Amount
Salaries
Project Manager(x1) | 17600
Business Analyst(x1) | 18400
Programmer/Developer(x1) | 24320
Systems Analys(x1) | 18000
Support Technician (x1) | 10000
Equipment (inclde software & hardware) | 3000
Traning | 5000
Facilities | 1000
Utilities | 3000
Travel/miscellaneous | 2000
Licenses | 1000
Total | 103320

## 2.3
Summary of Estimated Annual Operating Costs for Nami Sushi project
Recurring Expense | Amount(AUD)
IT support | 1500
Connectivity | 600
Training | 3000
Total | 5100

## 2.4
Estimated Annual Benefits
Bebefit/Cost Saving | Amount(AUD)
Reduced Waiting Time | 29200
Increased Customer Base | 75000
Enhanced Operational Efficiency | 30000
Improved Inventory Management | 6000
Total | 134200